## How to use
How to use this template
DEMONSTRATION PROJECT by Lizziewin Otero. Organization, names and figures are fictional.
1. Go to the Tasks sheet. White rows below the example tasks are ready for new entries.
2. Fill in ID, Task, Owner, Start and Due. Choose Priority and Status from the dropdown lists.
3. Do not type in 'Days left'. It is a formula: due date minus today. It is blank once a task is Done.
4. Row colors: red = past due and not done; yellow = due within 3 days; green = done.
5. The Summary sheet counts tasks by status and open tasks by owner. To add an owner, type the name in column A of the owner table.
6. The example rows show the expected format. Delete them when you start a real project.

## Tasks
Task and Project Tracker: Shared Drive Project
Brightwater Community Learning Center (fictional) · Days left counts from today's date
ID | Task | Owner | Priority | Start | Due | Status | % Done | Days left | Notes
T-01 | Draft shared-drive folder structure | Admin Assistant | High | 2026-10-05 | 2026-10-14 | Done | 100%
T-02 | Write file-naming guide (1 page) | Admin Assistant | High | 2026-10-08 | 2026-10-16 | Done | 100%
T-03 | Collect files from staff laptops | M. Santos | Medium | 2026-10-12 | 2026-10-23 | In progress | 60% | 5
T-04 | Set folder permissions for student records | A. Reyes | High | 2026-10-15 | 2026-10-21 | In progress | 40% | 3 | Restricted folder
T-05 | Get venue quotes for learners' showcase | J. Dela Cruz | Medium | 2026-10-08 | 2026-10-16 | In progress | 50% | -2 | One quote received
T-06 | Send November tutor schedule | R. Lim | Medium | 2026-10-14 | 2026-10-20 | Not started | 0% | 2
T-07 | Prepare Q3 attendance summary | M. Santos | High | 2026-10-09 | 2026-10-23 | In progress | 70% | 5
T-08 | Train staff on the shared drive (30 min) | Admin Assistant | Medium | 2026-10-26 | 2026-10-30 | Not started | 0% | 12 | At November meeting
T-09 | Archive 2024 paper records | Admin Assistant | Low | 2026-10-19 | 2026-11-06 | Not started | 0% | 19
T-10 | Order printed certificates for showcase | J. Dela Cruz | Low | 2026-11-09 | 2026-11-27 | Not started | 0% | 40
Formulas:
Days left = IF(OR([Due]="",[Status]="Done"),"",[Due]-TODAY())

## Summary
Summary
Counts update automatically from the Tasks sheet
Status | Tasks
Not started | 4
In progress | 4
Done | 2
Blocked | 0
Overdue (past due, not done) | 1
Total | 10
Owner | Open tasks
Admin Assistant | 2
A. Reyes | 1
M. Santos | 2
J. Dela Cruz | 2
R. Lim | 1